## 🐛 Issue Tracker
JASS — Issue Tracker ¦ V1 Code Review
ID | Title | Description | Module | Type | Severity | Reported By | Date Found | Assigned To | Deadline | Status | Notes
J-001 | animations.js not wired into game.js | animations.js defines functions (animateDeal, animateTrickCollect, etc.) but game.js never calls them. Cards have no deal/collect animation. | client/js | Improvement | Medium |  |  |  |  | Open | Easy win — just add calls in game.js event handlers
J-002 | Differenzler predictions lost on server restart | Predictions are stored in a module-level dict (_predictions). If uvicorn restarts mid-game, all predictions are lost. | server/game | Bug | High |  |  |  |  | Open | Move to GameState.scores or a new field
J-003 | Bot moves fire instantly — no delay | After a human plays a card, all bot moves execute synchronously. The client receives a burst of state updates with no time to animate. | server/bots | Improvement | Medium |  |  |  |  | Open | Add asyncio.sleep(0.8) between bot plays
J-004 | Trump picker doesn't show available Coiffeur modes | In Coiffeur, the trump picker shows all 6 modes even when a team has already played some. Player can accidentally pick a used mode. | client/js | Bug | Medium |  |  |  |  | Open | Pass available_modes in the game state view
J-005 | LAN server list not shown in lobby | lan_discovery.py and /api/lan/servers endpoint exist and work, but home.html has no UI to display discovered LAN servers. | client/templates | Improvement | Low |  |  |  |  | Open | Add a polling section to home.html
J-006 | No sound/settings UI in game.html | sounds.js has setSoundEnabled() and setSoundVolume() but there is no settings panel in the game HTML. | client/templates | Improvement | Low |  |  |  |  | Open | CSS for settings panel exists in phase11-additions.css
J-007 | Hand overflows on small mobile screens | On screens <380px wide, holding 9 cards causes the hand to overflow the viewport horizontally. | client/css | Bug | Medium |  |  |  |  | Open | Reduce card margin-left further or scale card size
J-008 | Weis (declarations) not implemented | Standard Schieber rules include Weis — declaring sequences or four-of-a-kind before play. Noted as deferred in Phase 3. | server/game | Feature | High |  |  |  |  | Deferred | Significant rule addition — needs design first
J-009 | No authentication on WebSocket | Any client can connect as any player_id. For LAN play this is acceptable; for public servers it is a risk. | server/sockets | Improvement | Low |  |  |  |  | Open | Simple token in /api/rooms response
J-010 | test_phase11.py uses hardcoded /mnt paths | Tests check file existence at /mnt/user-data/outputs/... which only exists on the build machine. | tests | Bug | High |  |  |  |  | Fixed | Fix with: sed -i s¦/mnt/.../¦¦g tests/test_phase11.py

## 📋 V2 Task Board
JASS — V2 Task Board
Task ID | Task Title | Category | Effort | Issue Ref | Owner | Start Date | Deadline | Status
V2-01 | Wire animations.js into game.js event handlers | Frontend | Low | J-001 |  |  |  | Not Started
V2-02 | Add settings panel HTML to game.html | Frontend | Low | J-006 |  |  |  | Not Started
V2-03 | Add bot move delay (asyncio.sleep) | Backend | Low | J-003 |  |  |  | Not Started
V2-04 | Highlight legal cards before selection | Frontend | Medium |  |  |  |  | Not Started
V2-05 | Show LAN servers in lobby | Frontend | Medium | J-005 |  |  |  | Not Started
V2-06 | Move variant state into GameState | Backend | Medium | J-002 |  |  |  | Not Started
V2-07 | Fix mobile hand overflow | Frontend | Low | J-007 |  |  |  | Not Started
V2-08 | Show available Coiffeur modes in trump picker | Frontend | Medium | J-004 |  |  |  | Not Started
V2-09 | Add Playwright end-to-end tests | Testing | Medium |  |  |  |  | Not Started
V2-10 | Rematch button after game_over | UX | Low |  |  |  |  | Not Started
V2-11 | Shorter room codes (4 chars) | UX | Low |  |  |  |  | Not Started
V2-12 | Score history chart per round | Frontend | Medium |  |  |  |  | Not Started

## 📅 Meeting Log
JASS — Meeting Log
# | Date | Type | Attendees | Key Decisions | Action Items | Next Meeting
1 |  | Kick-off |  | Assign code modules per member. Define V2 scope. | Fill issue tracker before next meeting.
2 |  | Code Review |  | Triage all issues. Assign V2 tasks to owners. | Each owner fixes assigned tasks.
3 |  | V2 Release |  | Demo V2 features. Run test suite. | Tag v2.0.0. Write changelog.

## 📖 Module Guide
JASS — Module Guide for Code Reviewers
File / Module | What it does | Key functions / classes | Depends on | Review focus
server/shared/types.py | All Pydantic data models. Single source of truth for Card, Player, GameState, etc. | Card, Player, Trick, Room, GameState, TrumpMode, GamePhase | pydantic | Model completeness. Are all necessary fields present? Any fields that should be Optional aren't?
server/shared/constants.py | Card point values, rank orders, deck composition, scoring constants. | TRUMP_CARD_POINTS, NORMAL_RANK_ORDER, TRUMP_RANK_ORDER, WINNING_SCORE | types.py | Verify Buur=20, Nell=14, last trick bonus=5, match bonus=100. Check rank orders.
server/game/deck.py | Build, shuffle, and deal the 36-card Jass deck. | build_deck(), shuffle(), deal(), deal_to_players(), remove_card() | types.py, constants.py | Does deal() use round-robin (real Jass)? Does remove_card() handle edge cases?
server/game/variants/schieber.py | Schieber rule implementation: trump selection, card ranking, legal moves, scoring. | card_rank_value(), get_legal_moves(), score_trick(), score_game(), is_buur(), is_nell() | base.py, constants.py | Buur exception in legal moves. Correct trump rank order. Obenabe/Undeufe modes.
server/game/variants/differenzler.py | Differenzler: individual predictions, penalty = ¦prediction - actual¦. | set_prediction(), get_prediction(), _compute_player_penalties(), is_game_over() | schieber.py (delegates card logic) | Predictions stored in module-level dict — lost on restart. Last-trick bonus included in actual?
server/game/variants/coiffeur.py | Coiffeur: each team plays all 6 modes. Repeat = doubled points. | record_mode_played(), is_mode_played(), get_available_modes(), on_round_start() | schieber.py (delegates card logic) | Mode tracking correct? Doubling only applies to trump-choosing team?
server/game/engine.py | Authoritative game loop. Only place where GameState is mutated. | start(), choose_trump(), play_card(), get_state_for(), start_next_round() | deck, rules, scoring, variants | Does play_card() correctly advance bots? Are hands hidden in get_state_for()?
server/game/rules.py | Move validation and turn helpers between engine and variants. | get_legal_moves(), validate_play(), assign_teams(), get_partner_id() | types.py, variants | Error messages descriptive? validate_play() check order (phase→turn→hand→legal)?
server/game/scoring.py | Apply scores to GameState, detect game over, summaries. | score_completed_trick(), apply_round_scores(), get_game_winner(), round_score_summary() | types.py, variants | Does apply_round_scores() correctly accumulate across rounds? Immutable (returns new state)?
server/bots/rule_based_bot.py | Heuristic Jass bot: trump selection, lead strategy, follow strategy. | choose_trump(), choose_card(), _lead(), _follow(), _discard_cheap() | types.py, constants.py | Does bot always return a legal card? Test edge cases (only one card legal, all trump, etc.)
server/rooms/room_manager.py | Lobby management: create/join/leave rooms, bot fill-in, game lifecycle routing. | create_room(), join_room(), fill_with_bots(), start_game(), play_card() | engine, bots, variants | Thread safety (plain dicts). Bot auto-trump after start_game(). Disconnection handling.
server/sockets/handlers.py | WebSocket event routing. ConnectionManager broadcasts personalised state. | handle_event(), ConnectionManager, broadcast_state(), _handle_play_card() | room_manager, events.py | Does _handle_play_card() correctly detect trick/round/game completion? Error propagation.
client/static/js/game.js | Game board rendering and state management. | initGame(), render(), onCardClick(), onTrickComplete(), showTrumpPicker() | socket.js | Is selectedCard state cleaned up correctly? Hand rendering on mobile.
client/static/js/socket.js | WebSocket client with auto-reconnect. | connect(), send(), on(), off(), getOrCreatePlayerId() | browser WebSocket API | Reconnect backoff correct? Player ID persistence in localStorage.
client/static/js/animations.js | Web Animations API — deal, play, collect, score, shake. | animateDeal(), animateCardPlay(), animateTrickCollect(), animateScoreReveal() | browser Web Animations API | Are these actually called from game.js? Test on Firefox (WA API support).

## 📊 Dashboard
JASS — Project Dashboard
Total Issues | Open | Fixed | Critical | V2 Tasks | V2 Done
Issues by Severity |  |  | Issues by Status
Critical |  |  | Open
High |  |  | In Progress
Medium |  |  | Fixed
Low |  |  | Verified
V2 Progress
Not Started
In Progress
Done
Blocked